# VP, PM’s, & Office Role Changes / Corrections

# Effective Immediately

# Immediate Corrective Actions:

- Every single project needs signed contracts by owners and our company; The only sticky one is Smash since we don’t have one and the current situation which is the cause of this document being made. However, every other job needs to reestablish a new updated contract that is to be approved in writing by Chase Landry & Bryan Bourque as a Master Template. We have Design-Build Contracts, Lump Sum, and Cost Plus so we need to ensure language is consistent in all and there are some slight provisions. Construction attorney already made these but we just need to double check for any provision needed in light of the last few months learning experiences.

- Michael Green cannot manage any project including FPK or Smash or any project without daily supervision from VP Bryan Bourque. More training must occur and testing passed prior to Michael being able to manage a project alone. We are currently creating an updated responsibilities list for the VP for this period of turmoil of change order handling. The responsibilities of the VP will be focused on Project Management oversight more heavily since that is the issue at this time that we cannot afford to make one more mistake. We will establish a “nice to have” vs “must be done” list for the VP and Chase Landry himself will take on any responsibilities left after from VP. One immediate action to change is that the VP go walk each project each Wednesday at the minimum to have good data for Thursday meetings, again until turmoil is resolved which is to be determined by Chase Landry.

# Roles & responsibilities

Project Manager (PM) — primary owner of job budget & forecast

- Build Estimate with real bids from subs and vendors, perform all takeoffs no matter if we are purchasing materials or not, and all estimates must be signed off by Chase, founder, and Bryan VP. This must occur prior to starting budget.

- Build baseline budget using AIA Schedule of Values from the estimate before work begins.

- Enter/attach all field time, POs, subcontractor invoices, change orders, and material receipts within 24 hours.

- Produce weekly reforecast and post to the shared job folder by Wednesday 12:00 PM.

- Attend weekly budget review with VP & Cost Accounting.

Cost Accounting / Office Manager (Controller) — verifier & reconciler

- Validate PM entries, code costs, and reconcile committed vs actual within 3 business days.

- Produce weekly variance report (line-level) and maintain job ledger.

- Lock/unlock budgets, post adjustments only after approval.

- Run month-end job close procedures and provide audit packet.

Vice President (VP) — governance, escalation & sign-off

- Approve budget baselines and any reforecasts that hit Yellow/Red triggers.

- Chair weekly budget review for red projects.

- Authorize corrective actions and performance remediation for PMs.

Office Manager / Data Input — document control & support

- Ensure source documents (invoices, POs, timecards) are scanned and attached to the job record.

- Maintain the KB and the SOP forms/templates.

Owner/CEO (you) — policy & consequences

- Approve thresholds and consequences, sign off on the remediation plan for the failing PM (below).

# Controls & tooling (single-source of truth)

- Budgets  Single source of truth: one project record in your PM/accounting system which is Procore Estimating. Then take final estimate and download into excel file to establish our budgeting system for now. There can be a simple few columns added to create a budget sheet that mimics Procore’s sheet. It will be stored in Excel in Sharepoint folders so changes will be tracked.  This budget will be in the Budget Folder in our Sharepoint files under each respective project. No parallel budgets. Just one singular budget with tracked changes. We are looking at Viewpoint or other options but for now we must establish a simple trusted system.

- Templates: one Budget Template, one Weekly Forecast template, one Change Order Request form, and one Budget Reconciliation checklist. These live in the Chase Group Sharepoint files folder.

- Locking: budgets are “locked” after VP sign-off. Only the Cost Accounting manager can unlock for a documented change order. Must have a signed Change Order from Owner (or representative) to be valid ABSOLUTELY NO EXCEPTIONS. Immediate termination is the penalty for not following this procedure.

# Step-by-step protocol (SOP)

### 1) Budget Creation & Baseline (Before mobilization)

- PM completes Standard Job Budget Template including contract value, line-item estimate (labor, material, subs, equipment, GC OH), contract driven contingency (5–10%) must be stated on contract schedule of values with thresholds, allowances, payment terms, schedule of values, and expected percent complete milestones.

- Cost Accounting reviews the budget for coding and math and ensures it imports into accounting/job cost.

- VP signs budget baseline. Once signed, budget is locked.

Deliverable: Signed Budget Baseline PDF attached to the job + digital entry in accounting.

### 2) Daily/Weekly Data Entry (Operational rule)

- Timecards: field personnel must submit daily timecards. PM ensures timesheets are posted to job within 24 hours.

- Invoices/POs/Subs: PM scans/attaches all invoices and POs and routes for matching within 24 hours. Controller posts to job cost within 3 days.

- Commitments: POs and subs are entered as commitments when issued and updated when invoiced.

### 3) Weekly Reconciliation & Forecast (Weekly cadence)

- Every Friday the PM produces a Weekly Budget Reforecast (one page): Actuals YTD, Committed, Forecast to Complete (ETC), Forecast at Completion (EAC), Variance vs Budget, % Complete, Key Risks/Action Items. Use the Weekly Forecast template.

- Controller runs a line-by-line reconciliation and attaches a reconciliation checklist; corrects coding errors or flags issues.

- If variance triggers are hit (Yellow/Red), the VP and PM schedule a mitigation meeting within 24 hours.

### 4) Change Order Control

- No changes to the locked budget without a Change Order Request (COR) form, justification, signed cost backup, and VP approval.

- Any amount of change is to be approved by owner unless we have a threshold stated in contract to dilute from Contingency bucket. There may be limits such as any number over $1,000 requires approval.

- No matter the cost of the Change, every financial change must be presented weekly to the owners unless they hit thresholds sooner which need approvals sooner than the particular day of the week such as our Friday updates. If for example, the threshold is $2,000 and the changes get to $2,001 or above prior to Friday then we need to get approval before filling up the contingency bucket gets diluted more. However, this is all contingent on the contract wording.

### 5) Monthly Close & Audit

- At month end Controller performs a formal job close check: invoice matching, retainage held, subcontractor reconciliation, tax accruals, lien waiver log, and realized/unrealized contingencies.

- Controller produces the Monthly Job Financial Pack: Budget, Actuals, Committed, ETC, EAC, Variance analysis, backup docs. VP reviews top 5 red projects monthly.

### 6) Escalation & Corrective Actions

- Yellow: PM creates action plan; Controller monitors; VP notified.

- Red: VP chairs mitigation meeting (action plan + timeline + named owners). If PM does not deliver corrective actions within agreed timeline, escalate to written performance improvement plan (PIP).

- Documentation of all decisions lives with the job.

### 7) Quarterly Audit & Continuous Improvement

- Cost Accounting performs quarterly audits of random jobs, and especially any job with persistent variance.

- Lessons learned from audits are added to the 03_Lessons_Learned folder and fed into training.

# Immediate remediation plan for turmoil (30 days)

Goal: Fix current errors and prevent future ones.

Day 0 (Immediate)

- Freeze new job sign-offs by the PM until baseline review is complete.

- VP orders an immediate audit of all active jobs. Cost Accounting produces a Job Financial Pack for each job within 4 business days.

30 days

- PM and Cost Accounting fix all coding/invoice/timecard errors found by the audit. PM attends daily 30 minute standup with Controller for corrections. Records documented.

- PM retrains on Budget Template and Change Order workflow (documented training session). PM passes a short test. Budget Template must be approved by Bryan Bourque as described in above in Controls and Tooling. Budget AIA Template must be approved also by Bryan for invoicing to clients.