1 — VP (Bryan Bourque)

Title: VP — Project Management Oversight 
Effective: Immediately

Role Summary
Act as the caretaker for PM oversight, daily updater of schedules & budgets, mentor to remediating PM(s), and final approver for escalations and budget sign-offs until PMs are fully cleared or new hires are in place.

Corrective Actions Management

Daily (every business day)

- 15–30 min morning roundup with PM(s): review critical tasks, RFIs, COs, site issues; record decisions in Task Register.

SOP Index Start

- Update master schedules for all active projects (progress %, crews, hold points, inspections); publish mid-day.

- Review daily budget snapshot: Actuals YTD, new commitments, recent invoices; note variances > threshold.

Corrective Actions Management

- Sweep Task Register: clear overdue items, ensure new tasks entered within 24 hours, reassign owners as needed.

SOP Index Start

- Pair with remediating PM (Michael): review his critical entries and sign off daily.

Weekly

- Walkdown: perform a weekly physical walkdown per project; reconcile field data & photos to reports.

PM Daily Schedule & Strategy SOP

- Approve/finalize Wed reforecasts; if Yellow/Red, chair mitigation meeting and define corrective actions.

Corrective Actions Management

- Lead weekly budget & variance meeting with PM(s), Shawnee, and Cost Accounting.

Ad hoc / As required

- Escalate/resolve RFIs > SLA (7 days) and hold architects/consultants accountable.

SOP Index Start

- Review & approve CORs; ensure Owner-signed CO exists before authorizing budget changes.

Corrective Actions Management

- Create/manage PM performance remediation & sign-off on competency.

Admin & Documentation

- Keep a short VP daily log per project (schedule & budget actions, decisions).

- Authority: final sign-off on baselines, reforecasts that hit Yellow/Red, and escalation approvals.

Quick VP Checklist (daily)

- Morning check-in complete.

- All projects’ schedules updated & published.

- Task Register sweep done (no new item > 24 hrs unentered).

SOP Index Start

- Budget snapshot reviewed; Yellow/Red items flagged.

- Michael paired & mentored; VP sign-off on his daily entries.

Acceptance
VP signature: ___________________ Date: _______

2 — Project Manager (Michael Green)

Title: Project Manager — Under VP Supervision
Effective: Immediately — no independent PM sign-off until retraining/test passed.

Corrective Actions Management

Role Summary
Continue full site/technical PM duties, but work under direct VP oversight. VP will co-sign or approve critical schedule and budget entries until remediation is complete.

Corrective Actions Management

Daily (every business day)

- Lead site operations: manage crews, enforce safety & hold points, coordinate subs.

PM Daily Schedule & Strategy SOP

- Prepare/upload daily report & photos at consistent time: 20 exterior + 20 interior.

SOP Index Start

- Upload source docs within 24 hours: timecards, POs, sub invoices, receipts. Notify VP of missing items.

Corrective Actions Management

- Draft RFIs, Submittals & CORs with full backup; submit to VP for review & routing.

Weekly

- Produce weekly reforecast (Wed 12:00 PM): Actuals YTD, Committed, ETC, EAC, Variance, %Complete, Top Risks & Actions. Provide backup.

Corrective Actions Management

- Prepare job packet for weekly budget meeting (open RFIs, CO pipeline, hold points, pay apps).

SOP Index Start

Remediation / Training

- Attend daily pairing with VP. VP must approve all critical schedule/budget entries.

Corrective Actions Management

- Complete retraining & pass competency test before independent management.

Quick PM Checklist (daily)

- Site & crew check.

- Daily report & 20/20 photo upload.

SOP Index Start

- All field documents uploaded (24 hrs).

Corrective Actions Management

- Draft RFIs/COs submitted to VP.

Acceptance
PM signature: ___________________ Date: _______

3 — Project Manager (Brandon Toney)

Title: Project Manager — Full PM Duties (VP verification on schedule & budget)
Effective: Immediately

Role Summary
Fully accountable PM for assigned projects. VP will verify daily schedule & budget updates; PM keeps primary responsibility for execution and hold point enforcement.

SOP Index Start

Daily (every business day)

- Lead site operations; pre-plan with Superintendent 3 days before scope start. Enforce hold points & QA.

SOP Index Start

- Produce daily report & photo set (20 exterior + 20 interior), upload at consistent time.

SOP Index Start

- Enter Task Register items within 24 hours; update status ≥ 2x/week. Coordinate schedule updates with VP.

SOP Index Start

Weekly / Monthly

- Weekly reforecast due Wed 12:00 PM; attend weekly budget meeting with VP & Controller.

Corrective Actions Management

- Coordinate with VP on Yellow/Red mitigation and prepare action plans.

Ad hoc

- Maintain detailed work orders with hold points and signed acknowledgements. Enforce subcontractor compliance.

SOP Index Start

Quick PM Checklist (daily)

- Site & safety check.

- Daily 20/20 photos & report.

SOP Index Start

- Task Register updated (24 hr rule).

- Ready reforecast backup.

Acceptance
PM signature: ___________________ Date: _______

4 — Office Manager / Controller (Shawnee Milburn)

Title: Office Manager / Controller — Verifier & Reconciler
Effective: Immediately

Role Summary
Control financial accuracy, COI & insurance compliance, invoice/pay app processing, job ledger reconciliation, and monthly audit packs.

Corrective Actions Management

Daily (every business day)

- Triage incoming invoices & pay apps: verify attachments and PM sign-offs; flag missing approvals. Route for action.

Corrective Actions Management

- Verify COIs & insurance before mobilization; upload to 02_Insurance & COIs; flag expirations 30/15/7 days.

Corrective Actions Management

Weekly

- Produce weekly overdue Task Register report for VP & PMs before weekly meeting.

SOP Index Start

- Run line-level weekly variance reconciliation after PM reforecast; prepare notes for VP review.

Corrective Actions Management

Monthly

- Perform month-end job close checks: invoice matching, retainage, subcontractor reconciliation, tax accruals, lien waiver log. Produce Monthly Job Financial Pack.

Corrective Actions Management

Ad hoc

- Lock/unlock budgets only per VP/Change Order policy; require documented Owner CO for unlocks.

Corrective Actions Management

Quick OM Checklist (daily)

- Confirm PM uploads for invoices/POs/timecards within 24 hrs.

Corrective Actions Management

- Run COI expiration flags & escalate.

- Send overdue report to VP & PMs.

Acceptance
Office Manager signature: ___________________ Date: _______

5 — Data Input / Document Control (Kaylin Miller)

Title: Data Input — Task Register & Document Control
Effective: Immediately

Role Summary
Single point for Task Register data input, file uploads, version control, weekly exports, KPI support, and final closeout uploads.

Corrective Actions Management

Daily (every business day)

- Ensure Task Register is up to date; link each task to supporting documents (RFIs, COs, invoices). Confirm PM uploads within 24 hours.

SOP Index Start

- Upload daily photo sets & reports; tag metadata and maintain audit trail for edits/uploads.

SOP Index Start

Weekly

- Produce Master Open Items export before weekly meeting and distribute to PM(s), VP & Shawnee. Update KPI dashboard: RFIs > SLA, open CO $ value, schedule variance.

Corrective Actions Management

Monthly

- Assist PM with closeout binder uploads to 09_Closeout; archive project documents and maintain Lessons Learned.

Corrective Actions Management

Ad hoc

- Audit Task Register compliance (24-hour rule, photo counts) and inform Shawnee/VP of persistent non-compliance.

Quick Data Input Checklist (daily)

- Task Register current & linked to docs.

SOP Index Start

- All daily photos & reports uploaded.

- Prepare Master Open Items report for weekly meeting.

Acceptance
Data Input signature: ___________________ Date: _______