Index Structure Starting Point - (no particular order….Chase here just dumping categories but the actual list will need to be ordered and placed properly)

- Potential Customer Contact Procedure

- Pre-construction Process

- New Construction procedure

- Renovations procedure

- Demolition Procedure

- Daily Management & Recording Procedure

- Project Manager Daily Duties per project

- Superintendent Daily Duties per project

- OM Daily Duties per project

- Estimator Duties Per Project

Potential Customer Contact

- Request specific information surrounding job type

- Request any plans that are complete or in process

- Send all information currently available about potential project to Chase for evaluation

- Schedule follow up with customer

Meeting with Customer regarding Project

- Discovery

  - Who, What, When Where, Why

  - Funding/Bonding

  - Property needs/property acquired

  - Contract type

  - Customer/Chase Group responsibility review

  - Discuss hiring of subcontractors directly by owner - Putting this in here for Cahee Job - Discuss delays outside of CG control and ramifications/liability not on CG, Discuss using subcontractors they would like to but them operating under CG MSA and Work Order so that we can establish control and better schedule the project thru completion

- Initial Agreement/Design Contract/NTP

  - Design/Estimating process; Discover all details, give budget bid

    - MEP is first, most important, takes time to get back and is typically largest cost -

    - Civil/Structural – Design of parking lot (topography), drainage, foundation, dirt pad, etc. Assessment from site work subs as well.

  - Final drawings and permitting complete, Give hard cost, get signature “Notice to Proceed” to solidify contract **All contracts/NTP’s -  submit to courthouse in city of jurisdiction of worksite**

  - Ensure no sitework, plumbing, electrical which usually begins immediately following NTP is started without discussing financing with owners, ensuring whether there are bonding requirements, or any specific bank requirements (Ref Luquette job where bank said they couldn’t prove there was no lien on property due to site work being performed even though we provided invoices to the bank showing subs were not unpaid, etc.)

Bare Essentials to initiate a project in pre-construction phase

- Must have email stating exact scope of work

- Must have a drawing attached whether it is hand drawn or markedup digitally by bluebeam or the like to express exactly what is being done; more detail the better in laymen’s terms and as technical as you can get. This is very important because a drawing and some detail can go a long way to end an argument of he said she said. This drawing has to be from Chase or Blaine but if Chelsea has direction she can also create something that we describe. Also Jacob or Blake can make a drawing but it has to be seen by Chase or Blaine to verify our promise matches that drawing.

- Must have lump sum price for work

- Must have exact day rates for each employee that would work on that project including OH for any additional work not named in the document if the job is time and material or emergency type of job that we absolutely don’t have any drawings or just need to selectively demolish or do something small.

- Also for time and material, have language about what items are billable such as fuel, small tools, delivery fees, office overhead etc that apply to that particular project

- Must have email approval to move forward with said project by acknowledging our email to move forward with terms stated. In our email, we need some language such as “ these are our terms and conditions, but if not acknowledged or approved by the time our workforce is physically working then it is assumed that all terms and conditions are accepted.

- A formal contract will be created and emailed to you in the near future but all work is being captured in our software Program Procore to provide updates as we make progress.

Preconstruction Sequence

- Things that happen no matter job type

  - Study drawings (war room)

  - Drawings must have details and/requirements for every scope of work to be performed that we are bidding on. If there are not drawings to show work that we are bidding, then we must supply such drawing from ourselves or a draftsman; draftsman needs to be paid for by customer if they want to hire…or the actual architect or whoever they had originally hired. However, these missing drawings or illustrations would always be submitted as RFI’s to the POR but we are just making sure any bids we provide sometimes without a POR present, we must provide a drawing or illustration in great detail so there is no gray area whatsoever…think lawsuit and having undeniable evidence on your side.

  - Submit RFI’s to POR, permit filings

  - A completed construction doc set should already have the board of health aka dept of health and hospitals packet submitted if required but it’s our duty to check to ensure it has been done not to delay permit being issued

  - Bid instructions to subcontractors *ensure MSA rules are followed and all information is explicitly stated by every means possible (i.e. highlight all metal studs, describe all details - submit RFI’s for anything that is not clear - ensure that the sub understands all details included in their scope of work so that past issues do not recur - Ensure that if sub’s work is on top of another’s (like finishing concrete floors)  they understand their responsibilities - Use photos, drawings, etc.)

  - Once subcontractors are selected, refer to sub contractor work orders/MSA for further information

  - Scheduling of continued inspections - front office/superintendent responsibilities and communication about scheduling etc. from beginning to end

- Things specific to New Construction jobs

  - Sitework, Plumbing, Electrical likely occurring at very early phase prior to permitting, etc.

    - Identify tap in sites for utilities

ii.       Site meetings must be held with subs for dirtwork/sitework, plumbing and electrical prior to beginning of work. Create a sign in sheet to record the site meeting. In the event that work orders have not been created (because we live in the real world and this can happen although it shouldn’t) ensure that drawings/photos, etc utilized to communicate process to subs are signed and dated at the point of discussion/at site meeting. Hold points must be discussed and expectations understood. Specific requirements per type of sub to follow….

b.      Site work specifics/Rip-rap site entrance

i.      Everything must be underground before parking lot including future conduits. Evaluate how far below grade on drawings is shown to bury pipes/conduits. Ensure it is far enough and always ensure that evidence recorded – photo/vido with measurements shown as to how far below grade pipes are buried.

ii.      Temp Power – get electrician out, set up power pole, etc. Turn on power

iii.      Plumbing – Water taps, meters, temp water, sewer

c.       Dumpster, Port-o-let, Container - get these things to job sites as needed, early on (Port-o-let will be needed as soon as people begin working on site but a dumpster/container may be delayed due to sitework being performed and those items becoming obstacles to site work ops) Evaluate daily to ensure these items are there as soon as or prior to being needed when possible.

d.      Site delivery planning

e.       Order Building

f.        Evaluate materials with long lead times, order all items possible

i. Order insulation, metal studs, strapping ASAP for building if metal building, Coordinate delivery because things will have to be ready on site for acceptance of these items

    - Interior doors typically have longer lead times as well as any exterior doors like metal roll up doors with windows (garage style, like fat pat’s or luquette)

g.      Scheduling of inspections

i. Include in schedule, list as many known inspections needed as possible up to and including end inspections for certificate of occupancy, board of health, fire marshal, etc. Make hold points for superintendent, OM, etc. to schedule them in advance

- Things specific to Reno/Demo Jobs

  - Execute agreements with owners * discuss hiring of subcontractors - work orders/MSA’s

  - Scheduling of inspections

    - Include in schedule, list all known - same as new construction, but there are job specific inspections

Subcontractors/Work Order requirements

- Scope of work

  - Work orders should be completed for each scope of work prior to that work beginning. (If one subcontractor is completing more than one scope of work, each scope should have it’s own work order.)

  - Hold Point(s) must be included in every work order without exception. At a minimum, end result should be a hold point regardless of scope.

  - Reviews of the work order with the subcontractor must be documented on a meeting log form.

  - The scope of work must be extremely detailed and include photos and reference to drawings regardless of the job type. Any supporting documentation included with the work order should be signed and dated by both the subcontractor and Chase Group.

  - Subcontractors must provide all tools to complete their scope of work  - Any tools provided by Chase group will be deducted as a rental from invoices submitted by the subcontractor.

  - Review and identify all hold points with the subcontractor and sign acknowledgement.  *Once all hold points for entire project have been established meet with owners to review and request any hold points they would want to sign off on?*

  - Penalties for hold point requirements, tools not being provided by the subs, etc. must be thoroughly explained and described within the work order.

Daily Management and Recording Procedure:

- Project Manager Duties -  Photos for Procore

- Every single day of each project there needs to be at minimum (20) photos of each project on the EXTERIOR of the project meaning the site grounds of soils, concrete, asphalt, green areas, entrances or anything the entire site, all sides of the structure, and perimeter of the property AND (20) of each project of the INTERIOR of the project meaning all rooms and spaces of the building. Photos need to capture all elevations of the interior meaning that there should be flooring photos and ceiling photos and inbetween to capture primarily the work of the day and secondarily work spaces that may not be worked on that day but need evidence of no work or if damages may have occurred. This also shows if a subcontractor has began work, continued, stopped work etc but this will capture evidence for reasons of enforcing our Master Service Agreement and possibly in the court of law.

- Photo capturing has methods for the purpose of getting up close to see the work for details but also to capture farther away to understand what exact location of the building you are located for back office reference but also future enforcement of photos.

- See the diagram ( CGSOP Photos - 101) for reference of the proper procedure of taking photos to capture the best angles of the work interior and exterior.

- Superintendent and PM must have a full conversation and face to face meeting about each scope of work 3 full days prior to the actual work being performed. Super must recite exactly what is going on, how it will occur, what materials, labor, timing, etc so that there are no surprises or questions once on the jobsite.

2. Framework for every single Scope of work for each project: PM, OM, & Super

- There are drawings to each scope of work of exactly how it needs to be constructed or performed. Drawings should fully describe the work and illustrate how it should be constructed with notes.

- If such drawings, or a portion or a detail, don’t exist then immediately there needs to be an RFI sent to Chase Landry, and PM so we analyze first then send on to architect, professional of record, or engineer depending who’s department is responsible. This RFI needs to be sent from Procore so it’s logged in Procore system and it’s a traceable thing. It can be sent on email but simultaneously be uploaded to the RFI section of Procore so it’s easier to just originate from Procore but both methods are acceptable. For the sake of clarity, a professional of record (POR) can actually be an engineer such as Chandler Staples that can draw and engineer and also submit to fire marshal so essentially he or any POR can act as an architect for purposes of providing more clarification to each scope of work if it does not exist.

- For CGC self-performed work: When drawings are fully described and all information is available to perform the work then the project manager must create a list of action items which can also be found in the work order for Chase Group so it is all documented the same no matter what. All action items need to be very detailed in a manner that the superintendent can understand exactly what is occurring and understand how to enforce such work. The actual method has to be described of how it will occur including timing, exact materials with an exact name brand material and quantities with exact sizing for each item. This is a PO along with backup documents such as sketches, photos, maps, etc to show the work in real life photos and layout things in clear manners prior to arriving at the jobsite. Use Bluebeam or markup program to overlay information over photos, drawings, maps, etc to fully illustrate the work so that someone unfamiliar can pick it up and read and understand. See Example @example (chase make one put here)

- For PO’s for our work make sure to create a checklist of each item on the drawing before sending to the vendor so that we capture our own quantities prior to them making a takeoff so we have something to compare to and reason why if we have differences (reference Dotd traffic control errors with LRH not having light arrows or enough “no shoulder” signs) This needs to be verified by someone who knows what the work entails aka the person reviewing this needs to have prior knowledge from physical experience or verify with a person who has physical experience such as Chase Landry if needed or subcontractor or professional in the field but don’t guess.

- A work order is created for CGC and the “subcontractor “ name in this case would be “CGC - (insert superintendent name). Now of course all of the legal language we have can be disregarded but the proper Hold Points language needs to be there with Hold point documentation to be signed in the same manner as subcontractors.

- For subcontractors work:

What is overall Responsibility of PM?

Manage project to be completed on time and on budget.

- Pre-construction expectations meeting with owner; responsibility matrix for all task including FFE, dumpsters, stickers, paintings on the wall, Utilities needed, etc…no stone left unturned. Target date to open.

- Work Orders w all subs and beat budget on project…maintain budget throughout project by only getting materials and subs by WO or Purchase Order.

- Pre-construction meeting with all subs and super

- Precise Schedule created and followed viciously daily - schedule has dates to have each Hold point to finish a subs work ( a subs work has to be done to call a job complete i.e. all of his equipment or work is completely finish and operates properly well before punchlist.

- Quality control via “Hold Point” documents signed by PM & Sub at each stage identified in Schedule

- Punchlist - written up by PM to be ruthlessly attacked each day and sent out each day to all email & text message reminders to make sure it’s done on time

- Handover C.O.